## Checklist tinh nang
STEADY — Checklist tinh nang theo tung man hinh (build tracker)
Uu tien: P0 = bat buoc cho MVP · P1 = nen co, co the lam ngay sau MVP · P2 = de danh cho v2. Cot Trang thai la o checklist — bam vao o va chon ☑ khi da hoan thanh.
STT | Hang muc can lam | Loai | Uu tien | Trang thai | Ghi chu
1. HOME (Main.dc.html)
1 | Header: logo Steady, badge streak, icon thong bao | UI | P0 | ☐
2 | Loi chao thay doi theo gio trong ngay + ngay/giai doan dieu tri | UI | P0 | ☐
3 | The CTA "Scan a meal" (mau cam terracotta) | UI | P0 | ☐
4 | 3 the Today's Progress (Fiber/Protein/Water) + thanh progress bar | UI | P0 | ☐
5 | Nut quick-add −/+ tren moi the + luu vao local DB | Logic | P0 | ☐ | Cap nhat UI ngay (optimistic), luu nen
6 | The Daily Dose (nhac lieu thuoc sap toi) | UI | P0 | ☐
7 | The "Any side effects today?" + nut Log | UI | P0 | ☐ | Moi them, khac biet hoa vs doi thu
8 | The Weekly Insight (tom tat nhanh) | UI | P1 | ☐
9 | Bottom nav 5 tab (Home/Scan/Insights/Community/Profile) | UI | P0 | ☐
10 | Tinh toan streak (so ngay lien tuc dat muc tieu) | Logic | P1 | ☐
11 | Load tong macro da log hom nay tu DB khi mo app | Logic | P0 | ☐
2. SCAN (Scan.dc.html)
12 | Xin quyen truy cap camera (runtime permission) | Logic | P0 | ☐
13 | Tich hop CameraX + khung viewfinder co goc bracket | UI/Logic | P0 | ☐
14 | Nut chup anh (shutter) | UI | P0 | ☐
15 | Trang thai loading trong luc cho AI phan tich | UI | P0 | ☐
16 | Goi Gemini 2.5 Flash/Flash-Lite API phan tich anh mon an | Logic | P0 | ☐ | Xem lai chi phi ~$0.0015-0.004/scan
17 | Xu ly khi AI khong nhan dien duoc mon an (fallback) | Logic | P1 | ☐
3. MEAL DETECTED (ScanResult.dc.html)
18 | Hien thi ket qua AI: ten mon, % do khop, anh chup | UI | P0 | ☐
19 | Luoi macro 2x2: Calories/Protein/Fiber/Carbs | UI | P0 | ☐
20 | Khoi tip lien quan GLP-1 (vd: high protein, de tieu) | UI | P1 | ☐
21 | Cho phep sua tay khi AI nhan dien sai mon/khau phan | Logic | P1 | ☐ | Fallback quan trong, tranh mat long tin
22 | Luu mon an vao nhat ky hom nay khi bam "Add to log" | Logic | P0 | ☐
4. LOG DOSE (LogDose.dc.html)
23 | The thong tin thuoc hien tai (doc tu ho so nguoi dung) | UI | P0 | ☐
24 | Chip chon vi tri tiem (Abdomen/Thigh/Arm) | UI | P0 | ☐ | CHI hien khi loai thuoc = Injection
25 | An hoan toan phan vi tri tiem khi loai thuoc = Pill/oral | Logic | P0 | ☐ | Dieu kien theo MedicationSettings
26 | Chon ngay & gio tiem/uong thuoc | UI | P0 | ☐
27 | O ghi chu tuy chon | UI | P1 | ☐
28 | Luu mui thuoc vao DB + cap nhat streak & the Daily Dose o Home | Logic | P0 | ☐
29 | Push notification nhac truoc gio tiem/uong | Logic | P1 | ☐ | De sau MVP dau tien
5. INSIGHTS (Insights.dc.html)
30 | Bieu do cot 7 ngay (mac dinh Protein) | UI | P0 | ☐
31 | The thong ke Streak + Avg. protein/ngay | UI | P0 | ☐
32 | Toggle chuyen doi giua Fiber/Protein/Water/Calories | UI | P1 | ☐ | Hien chi co Protein
33 | Bo loc xem theo tuan/thang | UI | P2 | ☐ | De v2
6. COMMUNITY (Community.dc.html)
34 | Danh sach bai dang: avatar, ten, badge thuoc+tuan dieu tri, noi dung, like/comment | UI | P1 | ☐
35 | Man hinh soan bai viet moi (nut "+" hien chua gan link) | UI/Logic | P1 | ☐ | Can thiet ke them
36 | Man hinh "Post Detail" (xem day du bai dang + danh sach binh luan + o nhap) | UI/Logic | P1 | ☐ | Chua thiet ke; la dich khi bam icon comment
37 | Data model Firestore: posts/{id}, subcollection likes/{userId}, subcollection comments/{id} | Logic | P1 | ☐ | Chua tao - can code moi CommunityRepository.kt khi bat dau man Community
38 | Logic Like: toggle qua Firestore transaction, tang/giam likeCount nguyen tu | Logic | P1 | ☐ | Tranh lech so khi nhieu nguoi bam cung luc
39 | Logic Comment: them doc vao subcollection + tang commentCount trong cung transaction | Logic | P1 | ☐
40 | Real-time listener cho feed va cho comments (Firestore snapshot listener) | Logic | P1 | ☐ | De UserB tu thay binh luan/like moi ma khong can refresh
41 | Nut Report tren bai dang/binh luan | Logic | P1 | ☐ | Buoc dau cua kiem duyet, gan voi muc kiem duyet ben duoi
42 | Gioi han so bai/binh luan moi nguoi dang duoc trong 1 ngay (chong spam) | Logic | P1 | ☐
43 | He thong kiem duyet noi dung (chan spam, thong tin y te sai) | Logic | P1 | ☐ | Quan trong ve phap ly/an toan
44 | Firestore security rules cho posts/likes/comments | Logic | P0 | ☐ | Chua tao - can viet firestore.rules khi bat dau man Community; khong co rules la ho toan bo du lieu
7. PROFILE (Profile.dc.html)
45 | Avatar, ten, loai thuoc dang dung | UI | P0 | ☐
46 | The thong ke: streak, ngay tham gia | UI | P1 | ☐
47 | Muc "Daily goals" -> DailyGoals | Navigation | P0 | ☐ | Da lien ket
48 | Muc "Medication & dose" -> MedicationSettings | Navigation | P0 | ☐ | Da lien ket
49 | Muc "Account" -> Account (sua thong tin, doi anh, log out, delete account) | Navigation | P0 | ☐ | Da thiet ke va lien ket
50 | Muc "Notifications" -> Notifications | Navigation | P0 | ☐ | Da thiet ke va lien ket
51 | Muc "Subscription" -> Subscription (paywall) | Navigation | P0 | ☐ | Da thiet ke va lien ket; uu tien vi lien quan truc tiep doanh thu
52 | Muc "Help" -> Help (FAQ + Contact support) | Navigation | P2 | ☐ | Da thiet ke va lien ket
8. LOG SIDE EFFECTS (SideEffects.dc.html)
53 | Chip chon nhieu trieu chung (Nausea, Fatigue, Headache...) | UI | P0 | ☐
54 | Thang muc do Mild/Moderate/Severe | UI | P0 | ☐
55 | O ghi chu tuy chon | UI | P1 | ☐
56 | Luu ban ghi trieu chung vao DB, gan theo ngay | Logic | P0 | ☐
57 | Canh bao/goi y lien he bac si khi chon muc Severe | Logic | P0 | ☐ | Quan trong ve an toan & phap ly
58 | Hien du lieu trieu chung tren Insights (bieu do xu huong) | Logic | P1 | ☐ | De sau, tai dung du lieu da co
9. MEDICATION & DOSE (MedicationSettings.dc.html)
59 | Chon loai thuoc: Injection / Pill-oral | UI | P0 | ☐ | Quyet dinh hien/an phan vi tri tiem o LogDose
60 | Nhap ten thuoc (Tirzepatide, Semaglutide...) | UI | P0 | ☐
61 | Nhap lieu luong hien tai (vd 5mg) | UI | P0 | ☐
62 | Chon tan suat: Weekly / Daily | UI | P0 | ☐
63 | Luu ho so thuoc, dung chung cho toan app (Home, LogDose, Profile) | Logic | P0 | ☐
10. ONBOARDING & SIGN IN (Onboarding1-3, SignIn.dc.html)
64 | 3 slide onboarding: gioi thieu app, Scan AI, Journey (teaser Premium) | UI | P0 | ☐ | Da thiet ke; anh huong truc tiep ty le dang ky
65 | Nut Skip / Next / Get started dieu huong dung thu tu | Navigation | P0 | ☐ | Da lien ket
66 | Bottom sheet Sign in - chi Google Sign-In (bo Apple, khong lam guest) | UI | P0 | ☐ | Da thiet ke
67 | Tich hop Firebase Auth + Google Sign-In SDK that | Logic | P0 | ☐
68 | Dieu huong: sau khi sign in thanh cong lan dau -> co the hoi Medication setup truoc khi vao Home | Logic | P1 | ☐ | Chua thiet ke buoc setup ban dau (loai thuoc/lieu/muc tieu)
11. SUBSCRIPTION (Subscription.dc.html)
69 | Danh sach 4 tinh nang Premium + 2 goi gia (Weekly/Yearly) + badge BEST VALUE | UI | P0 | ☐ | Da thiet ke
70 | Nut "Start 7-day free trial" -> tich hop Google Play Billing that | Logic | P0 | ☐
71 | Bat buoc nhap phuong thuc thanh toan khi bat dau trial (xem muc Ha tang chung) | Logic | P0 | ☐
72 | Man hinh nay mo duoc tu Profile > Subscription VA tu the Journey teaser o Insights | Navigation | P0 | ☐ | Da lien ket ca 2 duong
12. JOURNEY (Journey.dc.html)
73 | The preview lam mo (blur) + icon khoa + "Unlock your Journey" | UI | P0 | ☐ | Da thiet ke; co tinh gieo mong muon tu Onboarding slide 3
74 | Nut "Unlock with Premium" -> Subscription | Navigation | P0 | ☐ | Da lien ket
75 | Khi da Premium: chup/luu anh tien do hang ngay + bieu do can nang theo thoi gian | UI/Logic | P1 | ☐ | Chua build ban that vi dang bi khoa trong prototype
76 | Luu anh vao storage rieng tu (private), khong public len Community | Logic | P0 | ☐ | Du lieu nhay cam, can ma hoa/quyen truy cap chat che
13. DAILY GOALS (DailyGoals.dc.html)
77 | 3 the muc tieu Fiber/Protein/Water voi stepper -/+ | UI | P0 | ☐ | Da thiet ke
78 | Luu muc tieu tuy chinh vao ho so nguoi dung, dung chung cho Home/Insights | Logic | P0 | ☐
79 | Nut "Reset to recommended defaults" | Logic | P1 | ☐
14. NOTIFICATIONS (Notifications.dc.html)
80 | Danh sach thong bao nhom theo Today/Earlier, cham unread | UI | P0 | ☐ | Da thiet ke
81 | Nut "Mark all read" | Logic | P1 | ☐
82 | Backend gui push notification that (dose reminder, community like/reply, weekly insight) | Logic | P1 | ☐ | Trung voi muc he thong thong bao day o Ha tang chung
15. ACCOUNT (Account.dc.html)
83 | Doi anh dai dien, xem Ten/Email/Password | UI | P1 | ☐ | Da thiet ke
84 | Nut "Change" password -> luong doi mat khau that (hoac an di vi chi dung Google Sign-In) | Logic | P2 | ☐ | Neu chi dung Google Sign-In thi khong can mat khau rieng, nen bo dong Password
85 | Log out | Logic | P0 | ☐
86 | Delete account - xoa du lieu nguoi dung dung quy dinh (GDPR-like) | Logic | P1 | ☐ | Can xoa ca du lieu tren Firestore/Storage, khong chi tai khoan Auth
16. HELP (Help.dc.html)
87 | Danh sach FAQ tinh (co the mo rong dan) | UI | P2 | ☐ | Da thiet ke; noi dung mau, can viet lai cho dung san pham that
88 | O tim kiem FAQ | UI | P2 | ☐ | Hien chi trang tri
89 | Nut Contact -> mo email/form ho tro that | Logic | P2 | ☐
HA TANG CHUNG (khong rieng 1 man hinh)
90 | Dang ky / dang nhap bang Google Sign-In (Firebase Auth) - khong lam Apple Sign-In (Android-only), khong lam guest/an danh | Logic | P0 | ☐ | Da thiet ke man SignIn.dc.html
91 | Local DB (vd Room) luu du lieu log hang ngay | Logic | P0 | ☐
92 | Dung Firebase Firestore lam backend dung chung (feed, like, comment) - khong can tu dung server rieng | Logic | P0 | ☐ | Chua tao - can code moi CommunityRepository.kt + firestore.rules khi bat dau man Community
93 | Tich hop Gemini 2.5 Flash/Flash-Lite API cho AI scan | Logic | P0 | ☐
94 | Goi Gemini qua Cloud Function trung gian, KHONG goi thang tu app | Logic | P0 | ☐ | Tranh lo API key khi giai nen APK; Cloud Function giu key bi mat
95 | Xac thuc trang thai Premium qua Cloud Function + Google Play (server-side), khong chi tin co local tren client | Logic | P0 | ☐ | Chan viec can thiep app de tu bat Premium ma khong tra tien
96 | Xu ly Report/kiem duyet noi dung qua Cloud Function (khi can tu dong hoa) | Logic | P2 | ☐ | MVP co the xu ly thu cong truoc, tu dong hoa sau
97 | He thong thong bao day (nhac lieu thuoc, nhac log) | Logic | P1 | ☐
98 | Google Play Billing cho subscription tra phi | Logic | P0 | ☐ | Lien quan truc tiep doanh thu
99 | Bat buoc nhap phuong thuc thanh toan ngay khi bat dau dung thu 7 ngay | Logic | P0 | ☐ | Chuan Google Play trial; giam lam dung tai khoan ao, tu dong thu phi khi het han neu khong huy
100 | Gioi han so luong AI scan/ngay (vd ~8 scan/ngay) ap dung ca giai doan free/trial/premium | Logic | P0 | ☐ | Kiem soat chi phi API AI khi goi la "unlimited"; nang nguong sau khi co du lieu that
101 | Theo doi/canh bao khi 1 thiet bi hoac email tao nhieu lan dung thu lien tiep | Logic | P1 | ☐ | Chong lam dung ngan sach AI qua nhieu tai khoan ao
102 | Tich hop AdMob Rewarded Ads - xem quang cao de mo them luot scan khi cham nguong gioi han/ngay (chi trong free/trial) | Logic | P1 | ☐ | eCPM cao hon banner, nguoi dung chu dong chon xem, gan truc tiep voi co che gioi han scan
103 | Tich hop AdMob Interstitial nhe o diem chuyen man tu nhien (vd sau ScanResult, truoc khi ve Home), gioi han tan suat ~1/3-1/4 lan | Logic | P2 | ☐ | Tang doanh thu nhung can kiem soat tan suat de tranh gay kho chiu
104 | Khong dat bat ky loai quang cao nao o LogDose / SideEffects / cac man ghi nhan du lieu y te | Logic | P0 | ☐ | Bao ve trai nghiem o buoc nhay cam suc khoe
105 | Tu dong tat toan bo quang cao ngay khi user subscribe thanh cong (Weekly/Yearly) | Logic | P0 | ☐ | Giu dung loi hua tren man Subscription + tao dong luc nang cap
106 | Kiem tra chinh sach AdMob/Google Play doi voi app co du lieu suc khoe + khai bao SDK quang cao trong Data Safety | Logic | P0 | ☐ | Can lam truoc khi tich hop, tranh bi tu choi duyet app
107 | Tich hop Health Connect (buoc chan, hoat dong) | Logic | P2 | ☐ | Da quyet dinh de v2
108 | Backup / dong bo du lieu qua thiet bi | Logic | P2 | ☐